## MD Non Tech GTM Tracker
| GTM Template | [72 empty] | B2B Marketing | Y
[74 empty] | Onboarding | N
|  | BRD Requirement Details | [9 empty] | RACI Matrix |  |  |  | Tech Development Need |  |  |  | RACI Matrix |  |  |  | Content Need |  |  |  | RACI Matrix |  |  |  | Training and Communication Plan | [6 empty] | RACI Matrix |  |  |  | Capabilities Enhancement |  |  | Cost Benefit |  |  |  |  | Risk Mitigation Plan | [13 empty] | Go-Live Plan | [6 empty] | Closure |  | Listing
| Particulars | BRD Ref Number | BRD Date | Approved | Approved by | Approval date | Stakeholder / s | Stakeholder BU/s | Expected Impact Bu/s | Stakeholder/s Approved | Stk App Date | Responsible | Accoutnable | Consulted | Informed | Tech Requirement | Development Time Estimate | Development Start Date | Development End Date | Responsible | Accoutnable | Consulted | Informed | Content Creation equired | Content Created by | Content Approval | Content Approved | Responsible | Accoutnable | Consulted | Informed | Communication to end User | Internal Business Users to whom communication sent | Communication Sent date | Training Required | Training provided | Training I Date | Training C Date | Responsible | Accoutnable | Consulted | Informed | Capability Enahancement | Capability Enahancement Impact Areas | Capability Enhancement Measurement | Checked by | Cost Assigned to BU/s | Pass on by | Cost Approval | Approved by | Pre Launch Check List | UAT Reqd | UAT Conductyed by | UAT Date | Vetted by Stakeholders | Feedback Taken From | Feedback | Feedback Incorporated | Feedback Incoporation Date | Final UAT | UAT Conducted by | Final Sign Off | GTM Sign off | SVP Sign Off | Launch date | Post Launch Support Needed | Post Launch Support Provided by | Program Status | Post Launch Risk Assesment done | Post Luanch Risk Asesment done by | Remarks | Program Closure Date | Program Closure Comment | Activation
1 | Project Aqua | TBA | 2015-07-22 | Y | VC | July | Pradeep/ Arpan | Sellers Help | MD/MKT H | Y | July | See Line Items | See Line Items | See Line Items | See Line Items | [36 empty] | N |  |  | Y | GA/ SG | Seller Help Impact | Y | 31st July |  |  | N | N | N | 2015-08-04 |  |  | RTM |  |  |  | 25th Sept |  | Sellers Help
| Line Items : | [63 empty] | 2015-08-04 |  |  | RTM | [5 empty] | AM
a | Stakeholder Meet |  | 2015-07-23 | Y | VC | 23rd July | Pradeep/ Arpan | Sellers Help | MD/MKT H | Y | July | Pradeep/ Arpan | Anmol/ Mahesh | Gunjan/ Sanjay/ Vikas/ Shalini / Varun / Lokesh | Team Members | Y | BRAVO - Existing | BRAVO - Existing | BRAVO - Existing | Syatem Owner | Syatem Owner | Syatem Owner | Syatem Owner | [28 empty] | N | [9 empty] | Y |  |  | 2015-08-04 |  |  | RTM | [5 empty] | Ecosystem
b | Training Content |  | 2015-07-24 |  | GA | 24th July | Vikas Pandit | Activation | MD/MKT H | Y | 2015-07-28 | VP | VP | GA | Maruti | N | [7 empty] | Y | Maruti | VP/GA | Y | VP | VP | VP | Maruti | [20 empty] | N | [9 empty] | Y |  |  | 2015-08-04 |  |  | RTM | [5 empty] | Others
c | Emailer Content |  | 2015-07-23 | Y |  | 24th July | Shalini Srivastava | Activation | MD/MKT H | Y | 2015-07-28 | SS | SS | GA/ JS | Anmol Arora | N | [7 empty] | Y | SS | JS | Y | SS | SS | AA | PS / AS/ GA | Y | LM/VS/ GA/ VM/ SG/PS | 2015-08-04 | Y | [16 empty] | Y | SS | 3rd Aug | Y | AA | Post UAT | N | 3rdAug | Pending | SS | N |  |  | 2015-08-04 |  |  | RTM
d | Training F2F TOT |  | 2015-07-23 | Y | VC | 23rd July | Anmol Arora | Others | MD/MKT H | Y | 2015-07-28 | AA | AA | Arpan Saha | LM / BD / PS/GA/SG/VS | N | [18 empty] | Y | Y | 2015-07-29 | 4th Aug | AA | AA | Arpan Saha | PS/ GA/ LM/ VS/ | [9 empty] | N | [9 empty] | N |  |  | 2015-08-04 |  |  | RTM
e | Seller Help Impact |  | 2015-07-23 | Y | VC | 23rd July | Mahesh K | Sellers Help | MD/MKT H | Y | 2015-07-31 | MK/ Ajay | SG | Arpan Saha | AA/ PS | N | Existing Platform | Existing | Existing | Syatem Owner | Syatem Owner | Syatem Owner | Syatem Owner | [19 empty] | Y | Call Inflow # | Communication Via Intervals | [6 empty] | N | [9 empty] | Y |  |  | 2015-08-04 |  |  | RTM
f | ORM & Escalations Mgmt |  | 2015-07-31 | Y | VM | 31st July | Kanwardeep Singh | B2B Marketing | Enterprise | Y | 2015-07-31 | KDS | KDS | VM/ Arpan Saha | Sushant Kumar | N | NA | NA | NA | NA | NA | NA | NA | Y | KDS | WIP | N | KDS | KDS | VM | SK | N | [10 empty] | N | [8 empty] | N | [9 empty] | N
g
2
Line Items
a
b
c
3
Line Items
a
b
c